Status showing the progress of SFURTI clusters as on 12th August, 2016

| Sr. No. | Name of Cluster | Time line | Soft Intervention | Hard Intervention | Remark |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | CFC | Procurement of Machineries |  |
|  | State Office, Bangalore |  |  |  |  |
|  | Hudli Khadi Cluster | November, 2016 | Training completed on Skill Dev. for 50 Spinners and 25 Weavers | Work Order has been issued for construction of C.F.C. (3000 sq.ft) and construction work started & will be completed on 15.9.2016. | Procured 100 NMCs Order placed for 100 NMCs and 40 Looms with Udyog Bharati, Rajkot, Gujarat & expected by 31.08.2016 | Timeline will be met. |
|  | Sidlaghatta Khadi Cluster | September, 2016 | Training completed on Skill Dev. for 50 Spinners and 50 Weavers Awareness Prog. completed for 100 Artisans | CFC inaugurated on 27th July, 2016 by Chairman, KVIC. | Procured 100 NMCs, 12 semi auto looms, one warping unit and one cone winding machine and installed | Fully functional in Sept. 2016 |
|  | Harihara Khadi Cluster | September, 2016 | Training completed on Skill Dev. for 75 Spinners and 25 Weavers. 10 staff trained in Marketing | Renovation of work shed at New Chikanahalli (4000 sq.ft) is progress & will be completed by 31.8.2016 Date for inauguration of CFC – 2nd October, 2016 | Procured 100 NMCs. Order issued to Udyog Bharati, Rajkot, Gujarat for procurement of machineries | Timeline will be met. IA need working capital & requested for adjustment of IA share against land cost. |
|  | State Office, Hyderabad |  |  |  |  |
|  | Traditional Kalamkari Painting Cluster | November, 2016 | SHGs Training 200 Exposure visit -16 completed. 2 week TOT on SDP - 20 is going on. 10 days Trg on Marketing, 15 days Trg on Basic Accounting, 4 months in Design & Dev. Programma will be organized in Aug., 2016 | Tendering for construction of CFC will be issued on 19-08-2016 |  | Funds released on 28.07.2016 |

| Sr. No. | Name of Cluster | Time line | Soft Intervention | Hard Intervention | Remark |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | CFC | Procurement of Machineries |  |
|  | State Office, Chennai |  |  |  |  |
|  | Kangayam Khadi Cluster, Tirupur | September. 2016 | Training completed for Skill Dev. for 200 Spinners. Awareness Prog. Completed for 120 artisans | CFC is ready. Date for inauguration of CFC – 30th September, 2016 | 100 NMCs & 10 Looms procured on 9.08.2016 Blow Room Design | Showroom will be ready by 20.8.2016 Timeline will be met. |
|  | Steel & Wooden Furniture Cluster | December, 2016 | Trust building for 103 Artisans and 29 artisans trained under EDP. | Tender issued on 14.07.2016. Plan approval has been received. Work Order will be issued on 16.08.2016 Foundation stone laid down on 26.07.2016. | Plan for procurement of machineries, model, and specification is finalised. | Timeline will be met. |
|  | State Office, Ahmedabad |  |  |  |  |
|  | Blacksmithy & Agri Tools Cluster, Surat | December, 2016 | Training completed on Skill Dev. for 40 Artisan. Exposure visit organized for 5 Artisans | One CFC is Renovated. Work Order issued on 4.7.2016 for Construction of CFCs (1000 sq.ft). Re-tendering of another CFC issued on 20.7.2016 & Order placed on 6.8.2016 | Machineries less than Rs. 1 lakh cost procured. Tender will be issued and Order placed on 1.8.2016 Machineries expected in September, 2016 | Timeline will be met. |
|  | State Office, Bhubaneswar |  |  |  |  |
|  | Aabahana Fruit Processing Cluster | November, 2016 | 188 Artisans have been trained in Sensitation Training completed on Skill Dev. for 188 Artisans 188 artisans Trained under Capacity Building Exposure visit organized for 30 Artisans 15 Staff & CDE have been trained. | Tender for construction of CFC is finalized & will be issued in next week. | Tender for machineries is almost finalized & will be issued on 19th August 2016 | Funds released on 28.07.2016 |

| Sr. No. | Name of Cluster | Time line | Soft Intervention | Hard Intervention | Remark |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | CFC | Procurement of Machineries |  |
|  | State Office, Bhubaneswar |  |  |  |  |
|  | Jagmohan Brass & Bell Metal Cluster | November, 2016 | 300 Artisans have been trained in Sensitation SHGs Training completed for 300 Artisans 300 Artisans were Trained under Capacity Building Exposure visit organized for 30 15 Staff & CDE have been trained. | Tender issued for construction of CFC on 9.8.2016 | Tender issued for procurement of machineries on 9.8.2016 | Funds released on 28.07.2016 |
|  | State Office, Kolkata |  |  |  |  |
|  | Chak Islampur Khadi Cluster, Murshidabad | November, 2016 | Training completed on Skill Dev. for 40 Spinners & Weavers at NIFT, Kolkata | Tender issued for construction of CFC. Work order will be issued on 28.7.2016 | Plan for procurement of Charkhas has been completed. | Funds released on 28.07.2016 |
|  | State Office, Imphal |  |  |  |  |
|  | Ningomthong Reed Kauna Cluster | September, 2016 | Awareness Prog. for 150 artisans, 2 batches of SHGs for 250, 3 batches of Kauna Dyeing for 75, 2 batches of SDP for 115, Accounts & Marketing for 30, 2 workshops on Designing -60 | CFC is ready. Show room will be completed on 20.8.2016 Proposed for inauguration of cluster on 21-9-2016. | Supply order issued for procurement of machineries. | Timeline will be met. |
|  | State Office, Bhopal |  |  |  |  |
|  | Hoshangabad Bamboo Cluster, (M.P.) | October, 2016 | One day Work-shop for 300 artisans, Skill Dev. Trg. (4 weeks) for 30 Artisans, Cluster concept -118 Artisans | Tender issued for construction of CFC on 1.6.2016 and work order issued on 11.7.2016 and Construction work started. | Tender issued for procurement of machineries on 15.7.2016 | Timeline will be met. |
|  | Terracotta Cluster Patouhapura, Shahpur, Betul | December, 2016 |  |  |  | Fund to be received from Ministry |
| Sr. No. | Name of Cluster | Time line | Soft Intervention | Hard Intervention | Remark |
|  |  |  |  | CFC | Procurement of Machineries |  |
|  | State Office, Raipur |  |  |  |  |
|  | Bastar Handicraft Cluster, Bastar | November, 2016 | Sensitization -1021 Skill Develop -300 New Design -100 Capacity Building -100 | Construction of CFC is started. | Tender issued for procurement of machineries and will be finalized shortly. | Continuous down-pouring affects the construction work. |
|  | Dry Flower Cluster, Raipur | December, 2016 | Sensitization -250 Skill Develop -200 New Design -80 Exposure visit -30 Capacity Building -20 | Tender issued on 5.7.2016 for construction of CFC, however it was refused by L1 party. Order will be issued on 19th Aug. 2016. | Machineries will be procured only after completion of construction work of CFC. | Tender process is again started as the earlier tender got only 2 Quotations. |
|  | Div. Office, Varanasi |  |  |  |  |
|  | Hand Knotted Carpet Cluster, Allahabad | February, 2017 | Master Craftsmen completed Training at IICT 10 Artisans, Bhadohi & 80 artisans | Tender is likely to be issued on 25.08.2016 | Tender for procurement of machineries is likely to be issued on 25.08.2016 | Timeline will be met. |
|  | Divisional Office, Gorakhpur |  |  |  |  |
|  | Crochet (Croshiya) Cluster, U.P. | February, 2017 | Training completed on Skill Dev. for 220 Artisans | Tender for CFC completed. Work Order will be issued for construction of CFC in August | Order will be placed for procurement of machineries on 28.7.2016 | Timeline will be met. |
|  | Mau Pottery Cluster, Azamgarh | December, 2016 | Master’s Trainers Training Programme organized from 18.7.2016 at CVPI, Khanapur | Tender for CFC completed. Work Order will be issued for construction of CFC in August | Tender for procurement of machineries also floated on 28.06.2016. | Timeline will be met. |
|  | State Office, Ranchi |  |  |  |  |
|  | Santhal Paragana Silk Cluster, Jharkhand | December, 2016 / |  |  |  | Fund to be received from Ministry |
|  | Multi Products (Food processing & Beekeeping) Cluster | December, 2016 / |  |  |  | Fund to be received from Ministry |
|  | Koderma Agarbatti Cluster Jharkhand | December, 2016 / |  |  |  | Fund to be received from Ministry |